## Sheet1
To do Nightlight |  | V1.0 | V2.0 | V3.0
|  | 100% | 100% | 0%
Menu structure and button handling
| Implement three state machines: main state, top row, bottom row | 100%
| Port buttons from previous trial | 100%
| Class structure for states | 100%
| Implement how buttons affect each state | 100%
| Top row only visible if ‘menu’ is main state |  | 100%
| Bottom row only visible if item in top row is selected |  | 100%
| Find out mechanism to store simple handler functions |  | 100%
| Handler functions for each bottom row |  | 100%
| menuTimer to switch back to main state: clock |  | 100%
| Left and right buttons reset menuTimer |  | 100%
Light
| Smooth switching on/off |  | 100%
| Implement colors, check also at low power |  | 100%
| Smooth transition between colors |  | 100%
Clock
| Sync with WiFi to retrieve clock |  | 100%
| Implement clock in display |  | 100%
Cover up red power light from ESP |  |  | 100%
Additional timer to revive screen due to reset bug when menu changes |  |  | 100%
| Perhaps trigger 10 seconds after power on event |  | 100%
Find way to record power on event
Store project on Github |  |  | 100%
Move from Adafruit driver tu U8G2 driver |  |  |  | 0%
| Choose optimal font |  |  | 0%
| Optimize design |  |  | 0%
Other information
| Perhaps scroll weather, stock trading, or RSS news feed |  |  | 0%
| min scale | 0% | 0% | 0%
| max scale | 100% | 100% | 100%